## Earned_Value
ID | Active | Task_Mode | Name | BCWS | BCWP | ACWP | SV | CV | EAC | Baseline_Cost | VAC
0 | Yes | Auto Scheduled | Lab for Alex Kolar | 28860 | 24760 | 23485 | -4100 | 1275 | 27285 | 28860 | 1486.12744140625
1 | Yes | Auto Scheduled | Documentation | 9660 | 9360 | 9660 | -300 | -300 | 9660 | 9660 | -309.61563110351562
2 | Yes | Auto Scheduled | Identify existing skills | 2400 | 2400 | 2400 | 0 | 0 | 2400 | 2400 | 0
3 | Yes | Auto Scheduled | Identify needed skills | 1800 | 1800 | 1800 | 0 | 0 | 1800 | 1800 | 0
4 | Yes | Auto Scheduled | Develop training documentation | 4200 | 4200 | 4200 | 0 | 0 | 4200 | 4200 | 0
5 | Yes | Auto Scheduled | Distribute training manuals | 1260 | 960 | 1260 | -300 | -300 | 1260 | 1260 | -393.75
6 | Yes | Auto Scheduled | Trainers | 15400 | 15400 | 13825 | 0 | 1575 | 13825 | 15400 | 1575
7 | Yes | Auto Scheduled | Develop contract | 3600 | 3600 | 2400 | 0 | 1200 | 2400 | 3600 | 1200
8 | Yes | Auto Scheduled | Schedule classes | 2800 | 2800 | 2800 | 0 | 0 | 2800 | 2800 | 0
9 | Yes | Auto Scheduled | Hire trainers | 9000 | 9000 | 8625 | 0 | 375 | 8625 | 9000 | 375
10 | Yes | Auto Scheduled | Lab | 3800 | 0 | 0 | -3800 | 0 | 3800 | 3800 | 0
11 | Yes | Auto Scheduled | Secure lab space | 3800 | 0 | 0 | -3800 | 0 | 3800 | 3800 | 0
12 | Yes | Auto Scheduled | Sign lab contract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Yes | Auto Scheduled | Write progress reports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Yes | Auto Scheduled | Write progress reports 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Yes | Auto Scheduled | Write progress reports 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Yes | Auto Scheduled | Write progress reports 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Yes | Auto Scheduled | Write progress reports 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Yes | Auto Scheduled | Write progress reports 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Yes | Auto Scheduled | Write progress reports 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Yes | Auto Scheduled | Write progress reports 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Yes | Auto Scheduled | Write progress reports 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Yes | Auto Scheduled | Write progress reports 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0