## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Lab for Alex Kolar | 46.13 days | 10/1/14 8:00 AM | 12/4/14 9:00 AM |  | 0
1 | Yes | Auto Scheduled | Documentation | 14.75 days | 10/1/14 8:00 AM | 10/21/14 3:00 PM |  | 1
2 | Yes | Auto Scheduled | Identify existing skills | 3 days | 10/1/14 8:00 AM | 10/3/14 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Identify needed skills | 3 days | 10/1/14 8:00 AM | 10/3/14 5:00 PM | 2SS | 2
4 | Yes | Auto Scheduled | Develop training documentation | 3 days | 10/7/14 8:00 AM | 10/20/14 5:00 PM | 3FS+1d | 2 | Use PDF file format for documentation. Hire freelance help for writing. See if Ms. Leuke is available for the job.
5 | Yes | Auto Scheduled | Distribute training manuals | 0.02 hrs | 10/20/14 5:00 PM | 10/21/14 3:00 PM | 4 | 2 | Job well done!
6 | Yes | Auto Scheduled | Trainers | 12 days | 11/5/14 8:00 AM | 11/20/14 5:00 PM |  | 1
7 | Yes | Auto Scheduled | Develop contract | 3 days | 11/5/14 8:00 AM | 11/7/14 5:00 PM | 4 | 2
8 | Yes | Auto Scheduled | Schedule classes | 2 days | 11/12/14 9:00 AM | 11/14/14 9:00 AM | 7FS-1d | 2
9 | Yes | Auto Scheduled | Hire trainers | 3.88 days | 11/5/14 8:00 AM | 11/20/14 5:00 PM | 8 | 2
10 | Yes | Auto Scheduled | Lab | 43.13 days | 10/6/14 8:00 AM | 12/4/14 9:00 AM |  | 1
11 | Yes | Auto Scheduled | Secure lab space | 2.63 days | 12/1/14 1:00 PM | 12/4/14 9:00 AM | 9FS+1d | 2
12 | Yes | Auto Scheduled | Sign lab contract | 0 days | 11/20/14 5:00 PM | 11/20/14 5:00 PM | 11 | 2
13 | Yes | Auto Scheduled | Write progress reports | 41 days | 10/6/14 8:00 AM | 12/1/14 5:00 PM |  | 2
14 | Yes | Auto Scheduled | Write progress reports 1 | 1 day | 10/6/14 8:00 AM | 10/6/14 5:00 PM |  | 3
15 | Yes | Auto Scheduled | Write progress reports 2 | 1 day | 10/13/14 8:00 AM | 10/13/14 5:00 PM |  | 3
16 | Yes | Auto Scheduled | Write progress reports 3 | 1 day | 10/20/14 8:00 AM | 10/20/14 5:00 PM |  | 3
17 | Yes | Auto Scheduled | Write progress reports 4 | 1 day | 10/27/14 8:00 AM | 10/27/14 5:00 PM |  | 3
18 | Yes | Auto Scheduled | Write progress reports 5 | 1 day | 11/3/14 8:00 AM | 11/3/14 5:00 PM |  | 3
19 | Yes | Auto Scheduled | Write progress reports 6 | 1 day | 11/10/14 8:00 AM | 11/10/14 5:00 PM |  | 3
20 | Yes | Auto Scheduled | Write progress reports 7 | 1 day | 11/17/14 8:00 AM | 11/17/14 5:00 PM |  | 3
21 | Yes | Auto Scheduled | Write progress reports 8 | 1 day | 11/24/14 8:00 AM | 11/24/14 5:00 PM |  | 3
22 | Yes | Auto Scheduled | Write progress reports 9 | 1 day | 12/1/14 8:00 AM | 12/1/14 5:00 PM |  | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Hans Hawke | HH | Work |  | TR2 |  |  | 100% | $100.00/h | 0
2 | George Booth | GB | Work |  | TR2 |  |  | 100% | $75.00/h | 0
3 | Manuals | Man | Material | [5 empty] | $30.00 | 0
4 | Helene Park | HP | Work |  |  |  |  | 100% | $50.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Identify existing skills | Hans Hawke | 1 | 24h | 100%
Identify needed skills | George Booth | 1 | 24h | 100%
Develop training documentation | Hans Hawke | 1 | 24h | 100%
Develop training documentation | George Booth | 1 | 24h | 100%
Distribute training manuals | Hans Hawke | 1 | 8h | 100%
Distribute training manuals | Manuals | 1 | 10 | 10
Develop contract | Hans Hawke | 1 | 24h | 100%
Schedule classes | Hans Hawke | 1 | 16h | 100%
Schedule classes | George Booth | 1 | 16h | 100%
Hire trainers | Hans Hawke | 1 | 31h | 100%
Hire trainers | George Booth | 1 | 31h | 100%
Hire trainers | Helene Park | 1 | 24h | 100%
Secure lab space | Hans Hawke | 1 | 16h | 100%
Secure lab space | George Booth | 1 | 16h | 100%