## Task_Table
ID | Name | Duration | Start | Deadline | Resource Names | Notes
1 | Measure existing space | 7h |  |  | Phil Dunbari | Provide tolerances
2 | Create floor plans | 2d |  |  | Claire Diaz | Use AutoCad
3 | Diagram electric and HVAC | 3d |  |  | Mitch Cameron | Verify town codes
4 | Plan furniture layout | 2d |  |  | Claire Diaz, Phil Dunbari | Discuss budget
5 | Plan wall and floor coverings | 3d |  |  | Claire Diaz
6 | Wire diagrams for networks | 3d |  |  | CoopCommunications | Check current capacity

## Info_Table
Microsoft Project | Template ID: | 4535923402 | (Do Not Edit)
Project is a project management program designed to help you plan, manage, and communicate your projects.
Whether you have a simple list of tasks or want to coordinate activities across multiple projects, Project makes it easy to get started and learn as you go.
This template has been designed to help you to get started in Excel, but when you need more like:
* See your tasks in a Gantt Chart
* Create links between tasks so one task starts after another task finishes
* See how much work each person on the team has assigned to them
You can easily import this information into Project and keep working.